## Table 1
Item | Asset | Consideration | Hazard / Aspect | Incident / Event | Consequence / Impact | Existing Controls/ Monitoring and Assessment undertaken | Additional Controls, monitoring , assessment or actions required | MRM Response / Actions
1 | OEF | Geochemical | Failure of NOEF cover. | Current cover design insufficiently robust to control acid, saline and metalliferous drainage in perpetuity. Cover breached through erosion, slumping, differential movement, and/or undermining of dump due to extreme flooding event. | Acid, saline and metalliferous drainage impacts on groundwater, terrestrial and aquatic ecosystems. | A cover design has been produced based on new waste rock geochemical classification and materials available. | The current cover design relies on the perpetual performance of a 0.6m compacted clay layer. Given the highly pyritic nature of the waste rock and the size of the dump, the thin nature of the oxidation/infiltration control layer appears disproportionate and sensitive to erosion, slumping, differential movement and flood effects. The long term stability of the current dump design should be reviewed, and trial dump cover areas established. The batters tend to have a higher erosion risk, and the design should ensure at a minimum that PAF-­‐HC and PAF-­‐RE are excluded from below batter zones and set back 100m from the outer face. Review geochemical classification criteria and identify opportunities to increase the amount of lower acid/salinity/metal leaching material and increase the robustness of the dump cover. Review opportunities to further segregate mine materials during mining based on more detailed geological differentiation. | a) The URS cover design that is the current approved cover has only a 0.7m thickness of material over the compacted clay layer (CCL). MRM has been working with O'Kane Consultants on revising he cover design through 2013 and 2014. This included landform and erosion modelling for a period of 1,000 years. Their assessment was that the URS cover would be insufficient to maintain saturation and low permeability of the CCL. Preliminary modelling indicated thicker NAF coverings and alternate landform shapes would be required. This work will continue in 2014 and 2015 as part of the EIS. b) Work on the cover design has been in progress through late 2013 and 2014. This was part of the original plan to conduct a rehabilitation trial and lysimeter/instrumentation on a section of the NOEF in 2014. However, the EIS process has halted the field trials until further study is completed and the mine has an approved MMP. c) Whilst all options will be investigated, it is considered unlikely that it would be possible to exclude PAF from under the batter zones of the dump. Excluding PAF material from this area would require a much larger dump, which then has a larger catchment area, thereby increasing potential seepage, disturbance and water course diversions. An alternative dump cover concept features a much greater thickness of clean benign NAF with concave slopes to form the batters, based on erosion modelling over a 1,000 year modelling period, to provide protection for the PAF core and its encapsulating CCL. The on-going EIS work will further refine the trade-off of dump height, batter slopes and geometry to arrive at a solution that will perform for the long term. d) An independent external review of the geochemical classification criteria has already been conducted. It found no possibility of increasing the sulphur cut-off of the benign waste types to increase the amount available. The EIS is conducting further drilling and geochemical tests to better define the resources of all waste types both in the pit and on the lease to ensure that the proposed waste dump solution has the materials available to construct it. It is recognised that there is insufficient benign NAF in the current final pit to construct a robust final cover, so investigations into extending the pit within the levee wall are being conducted to meet the requirements of a stable dump in the long term. e) Studies into selective mining of the waste rock to optimise clean NAF resources and minimise quantities mined as PAF are occurring, and will be updated when the results of further drilling are incorporated into the block model and digital surfaces. The future mining fleets planned all feature hydraulic excavators rather than face shovels so that 4-5m high benches can be mined where required rather than 16m high benches.
2 | OEF | Geochemical | Poor or partial performance of cover. | Cover design fails to control infiltration or oxygen flux or both leading to poor or partial performance of cover. | Acid, saline and metalliferous drainage impacts on groundwater, terrestrial and aquatic ecosystems. | Cover design performance modelling by two different consultants. | Clarify the primary purpose (infiltration control or oxidation control) and performance of the cover system and uncertainties as it applies to site conditions and available materials. Carry out instrumented cover trials to check construction methods and performance. | a) A Failure Modes and Effects Analysis (FMEA) was conducted in Darwin with a multi-disciplinary team to test the possible failure modes of the dump and cover system. Many potential risks were identified that will be addressed in the EIS. The field works beginning for the EIS are collecting additional data on material characteristics and their variability, and site conditions and how they vary in different areas. This will increase the confidence in the ability of MRM to execute the designs in the field with a high probability of success. b) MRM want to seal off and rehabilitate the existing PAF cell at the NOEF as soon as possible to reduce infiltration and seepage from this part of the dump. Information on instrumentation and a lysimeter was submitted to the DME in late 2013 with a view to construct the system through 2014 and 2015, demonstrating MRM's commitment to successfully designing, constructing and closing completed sections of the dump. Some equipment has already been purchased. However, the constructions are now waiting on advancement of refined designs being undertaken as part of the EIS. Once the most likely dump construction designs and methods are identified, opportunities to commence field trials will be investigated.
3 | OEF | Geochemical | Insufficient NAF materials for NOEF cover. | The cover is compromised due to a shortfall in the required NAF materials. The current cover design requirements for NAF materials is closely balanced with estimated available volumes, but there is potential for shortfall due to issues with recovery, the preliminary nature of the geochemical | Acid, saline and metalliferous drainage impacts on groundwater, terrestrial and aquatic ecosystems. | Estimates of geochemical materials to be mined based on preliminary criteria for new geochemical categories. | Review geochemical classification criteria and identify opportunities to increase the amount of lower acid/salinity/metal leaching material and increase flexibility. Progress full incorporation of new geochemical categories into distribution model. Review opportunities to further segregate mine materials during mining | a) It is not clear to MRM what this statement is suggesting, so please forgive a mis-guided answer. An independent external review of the geochemical classification criteria has already been conducted. It found no possibility of increasing the sulphur cut-off of the benign waste types to increase the amount available for use in the cover. The EIS is conducting further drilling and geochemical tests to better define the resources of all waste types both in the pit and on the lease to ensure that the proposed waste dump solution has the materials available to construct it. It is recognised that there is insufficient benign NAF in the current final pit to construct a robust final cover, so investigations into extending the pit within the levee wall are being conducted to meet the requirements of a stable dump in the long term. b) The geological model was updated with the new classification criteria in Q1 2014. Once the results of the 2014 drilling program are available, the model will be updated. c) Studies into selective mining of the waste rock to optimise clean NAF resources and minimise quantities mined as PAF are occurring, and will be updated when the results of further drilling are incorporated into the block model and digital surfaces. The future mining fleets planned all feature hydraulic excavators rather than face shovels so that 4-5m high benches can be mined where required rather than 16m high benches. Drilling programs to find and/or confirm the quantities and location of NAF materials are underway as part of the EIS. Alternative pit designs to target near-pit clean NAF resources are being planned. The extra mining and associated costs for finding suitable quantities of suitable NAF resources will be incorporated into the financial assessment of the various options. Separate dumps that have a larger surface area to stored volume ratio are likely to be dropped from future mine plans to reduce the amount of NAF required to close the dumps permanently.
4 | OEF | Geochemical | Misclassification of geochemical rock types. | Classification criteria preliminary and not fully integrated into the geochemical distribution model and field reconciliation, compromising material segregation and leading to placement of geochemical rock types in the wrong locations. | Acid, saline and metalliferous drainage from unexpected parts of the dump and consequent impacts on groundwater, terrestrial and aquatic ecosystems. Inefficient use of the limited NAF materials in non key zones. | Studies and assessments carried out in conjunction with KCB and preliminary criteria established. Leach barrel tests set up on site. | Continue investigations to develop criteria. Continue leach barrel testing. Set up leach column testing of a variety of materials as recommended by KCB (2014a). Column tests are operated under more controlled laboratory conditions, and are easier to interpret and will assist assessment of leach barrel tests. | a) The criteria have been reviewed with the findings being considered at present. MRM are further refining the methods to identify and segregate the various waste types in the field. b) The barrel leach tests are continuing. New column tests have been planned, with sample collection occurring in October 2014 with the mobilisation of drill rigs and field personnel.
5 | OEF | Geochemical | Misplacement of waste rock materials. | Materials placed in the wrong locations due to: a lack of geochemical material tracking; use of the older classification system in historic dump area; and use of older classification in NOEF NAF material checks. | Acid, saline and metalliferous drainage from unexpected part of the dump and consequent impacts on groundwater, terrestrial and aquatic ecosystems. Inefficient use of the limited NAF materials in non key zones. | NOEF NAF material checks. Dispatch system. | Implement system for tracking of waste rock geochemical and lithological types placed in the NOEF. Review old dump areas and potential issues associated with mis-­‐ classification. Modify NOEF field checks to reflect new geochemical criteria. | a) MRM has already got a new mine management system called APS operating that features GPS tracking of materials from the pit to the dump. Zones and codes are set up such that if an operator tries to dump material in an unauthorised location, alerts will be triggered. The Production Engineers check the logs each day for breaches that may need rectification. MRM is currently working with APS to develop a means to create an as-built 3 dimensional model of the dump that would show the material types in real space. b) A review of the old dump areas was completed by MRM and sent to the DME in May 2014. A review of the dump sampling data indicated a very low proportion of PAF materials incorrectly dumped in the NAF areas. The incorrect as c) The NOEF field checks were revised earlier in 2014 to increase the density of samples of NAF (now 1 sample per 100,000t mined) and also include sampling of PAF at the rate of 1 sample per 50,000t mined. MRM typically mines 80,000 to 100,000t of waste per day.
6 | OEF | Geochemical | Development of convection cells in end tip dump areas. | End dumping of PAF materials resulting in segregation of coarse and fine materials and creation of chimney structures that encourage rapid convective oxidation. | Greater rates of oxidation and generation of acid, salinity and dissolved metals, consequent impacts on groundwater, terrestrial and aquatic ecosystems. Spontaneous combustion impacts from reactive PAF. | Future reactive PAF will be paddock dumped and traffic compacted, but end tipping is still planned for other PAF materials. | Extend paddock dumping to PAF-­‐HC in addition to PAF-­‐RE, or devise an equivalent construction method that prevents development of coarse chimney structures. Control convection in old dump areas by placement of paddock dumped (or equivalent) materials on the outer face with (ideally) a minimum 100m horizontal thickness. | a) Dump lift height for the proposed Central West stage to be constructed during the EIS period will be a maximum of 5m for PAF materials, with identified reactive PAF being paddock dumped. The batters will be pushed down to 1:4 progressively as the dump is raised. These methods have been used in the new PAF cell of the NOEF built in 2014, with superior results to the higher lifts. The EIS will look to find the optimal lift heights for all dumped materials. b) Dumping of NAF in low-lifts is almost complete on the eastern side of the PAF dump. The northern face, which is most exposed to the prevailing winds, will be ready for dumping in September 2014. Dumping in front of the southern and western faces of the NOEF PAF cell will be with NAF materials when they are available. The optimum thickness and lift heights of this zone are key investigations of the EIS that is currently in progress.
7 | OEF | Geochemical | Spontaneous combustion. | Materials historically placed without controls and new materials not sufficiently managed combust and leave voids and weaknesses. Planned spraying of combusting materials with water containing hydrated lime accelerates the reaction and increases the impact. | Spontaneous combustion affects the stability of the NOEF and results in breaches the of the final cover, and causes release of acid/saline/metalliferous drainage, impacting groundwater, terrestrial and aquatic ecosystems. | A KCB review of existing zones of spontaneous combustion has been carried out and remediation approaches recommended. MRM plan to apply water and hydrated lime to existing spontaneous combustion. | Follow KCB recommendations and finalise methods of spontaneous combustion control. Avoid the planned application of water and lime, or trial on a small area before widespread use. | a) MRM have been undertaking extensive works on the NOEF in the dry season of 2014 to remediate areas of spontaneous combustion. This has included dozing and excavating hot material out of the dump before spreading and compacting it in thin layers. b) Mixtures of hydrated lime and water have been used to spray hot spots in some places. MRM's independent geochemical advice is that, at the water to lime ratio's used, the water in the mix will not be problematic, with most evaporating off the hot rocks rather than further enhancing the reaction. MRM will continue to revise practices used to prevent and remediate spontaneous combustion in the pit and waste dump. This includes investigating alternative chemical compounds that MRM have been made aware of that may be able to halt the exothermic reactions.
8 | OEF | Geochemical | Spontaneous combustion. | Mis-­‐placement or poor identification of reactive PAF leading to spontaneous combustion. | Spontaneous combustion affects the stability of the NOEF and results in breaches the of the final cover, and causes release of acid/saline/metalliferous drainage, impacting groundwater, terrestrial and aquatic ecosystems. | Geologist believe the Black Bituminous Shale in the NE corner of the pit has the highest spontaneous combustion potential, and are working with KCB to develop criteria | Continue investigations to develop criteria. | a) Investigations conducted during 2014 identified that spontaneous combustion at MRM is linked to shales with a sulphur content over 10%. These areas have been flagged in the block model as being reactive PAF. MRM has a procedure in place through 2014 to check the temperatures of all drillholes in areas and rock types that have previously been identified as prone to spontaneous combustion, as well as the areas newly flagged in the block model. This enables a more detailed map of local heating zones to be identified so that appropriate blasting, loading and dumping practices can be applied to the at-risk materials.
9 | OEF | Geochemical | Pyritic waste rock materials exposed during operations prior to placement of final cover. | No interim capping of waste rock surface and no progressive rehabilitation leads to oxidation of pyritic materials. | Acid, saline and metalliferous drainage impacts on groundwater, terrestrial and aquatic ecosystems. | Reference to interim 0.6m clay layers made in MMP (MRM 2013a), but not clear is this is being implemented. | Cover should be progressively placed as soon as completed waste dump area become available, and interim caps should be placed over active PAF dump areas prior to each wet season. | a) MRM re-affirm their commitment to place lower permeability liners on PAF cells exposed at the end of the dry season. KCB provided a report recommending specifications of these liners and some alternatives to using clay if clay is in short supply. The program for capping the finalised sections of PAF cells in 2014 is behind schedule due to delays in government approvals associated with the specifications of clay used in liners. MRM are working to resolve these issues as soon as possible to complete as much capping as possible before the 2014 wet season commences. Improved QA/QC processes were identified in 2013 as being required to ensure the as-built CCL's match the specifications required. This has seen MRM contract out CCL placement to specialist contractors in 2014. On-going contract CCL construction has been factored into the site budgets.
10 | OEF and TSF | Landform Stability | Potentially acid forming, saline and neutral mine drainage waste rock. | Compacted clay layer exposed to drying and/or erosion leading to failure of cover system. | Acid, saline and neutral drainage impacts terrestrial and aquatic ecosystems. | Nil | Undertake erosion and sediment transport modelling of the proposed NOEF landform to identify depth of NAF cover material required to ensure the functionality of the cover for 100, 500 and 1,000 years. | a) This modelling has already been completed in Q1 2014 by O'Kane Consultants. Further materials classification samples are being gathered and tested to better understand the variability in materials to be used in the cover system, so that the design has a high probability of success and is robust over a range of expected site conditions. There is a testing program currently in operation that is measuring the drying front through a test CCL to better understand drying/desiccation depths over time. This will be used to refine the thickness of the clay liner and the time before it is covered with protective materials.
11 | TSF | Geochemical | Tailings leachate from Cell 1 | Poor design of TSF and incomplete rehabilitation of Cell 1 leads to TSF leachate into surprise creek. | Water quality (mainly elevated SO4 salts and electrical conductivity) impacts on groundwater, terrestrial and aquatic ecosystems. | Shallow cut-­‐off barrier, seepage interception sump. Monitoring of surface water and groundwater. Placement of 0.5m clay cap on cell 1 for dust control. Geophysical analysis to track saline plumes. Aquatic fauna surveying in Surprise Creek. | Complete interim clay cover (O’Kane Consultants). Install planned decant towers. Schedule reprocessing of Cell 1 tailings as planned to eliminate the hazard. | Planned actions for 2014 include: • Works to repair the interim drainage works to mitigate overflows from Cell1. • A drilling program around the TSF aimed to identify preferential pathways and determine hydrogeological parameters to assist development of effective seepage mitigation structures and hydro geochemical modelling of the TSF. • Installation of piezometers within the tailings of Cell1 to allow monitoring of the phreatic surface in Cell1 to assist understanding of seepage and infiltration processes and modelling. The cores will also be stored for later geochemical analyses. Planned actions for 2015 include: • Improvements of cover drainage design as necessary. • Undertake hydrogeological and hydro geochemical modelling of the TSF with emphasis on Cell1 and Surprise Creek. • Installation of seepage mitigation measures developed from 2014 seepage investigation. • Development of cover trials on Cell1.
12 | TSF | Geochemical | Tailings leachate from Cell 2 | Leachate reports to groundwater and ultimately to surface drainage down-­‐gradient. The currently detected leakage in ground water is presumably due to breaches in the Cell 2 clay foundation, and the interception trenches on eastern and western sides being too shallow to pick up all seepage. At closure this leakage may occur due to failure of final cover though erosion or slumping etc. and/or inadequate performance of cover as designed. | Water quality impacts on impacts on groundwater and surface drainage down-­‐ gradient. Short Term -­‐ mainly elevated SO4 salts and electrical conductivity Longer Term -­‐ acid and elevated metals once tailings acidify. | Monitoring of groundwater. Shallow Interception trenches. | Further geochemical characterisation of tailings to better understand acid, saline and metal/metalloid leaching potential and variation. Include routine testing of discharged tailings and historical (deposited) tailings. Kinetic test work to understand leaching characteristics including lag times before generation of ARD. Investigate cause of current seepage, assess potential impacts and undertake remedial action as required. Produce a final TSF cover design. Carry out field trials of cover design and measure performance against design. Include assessment of long term erosion and stability effects on the cover integrity. | Planned actions for 2014 include: • Works to repair the interim drainage works to mitigate overflows from Cell1. • A drilling program around the TSF aimed to identify preferential pathways and determine hydrogeological parameters to assist development of effective seepage mitigation structures and hydro geochemical modelling of the TSF. • Installation of piezometers within the tailings of Cell1 to allow monitoring of the phreatic surface in Cell1 to assist understanding of seepage and infiltration processes and modelling. The cores will also be stored for later geochemical analyses. Planned actions for 2015 include: • Improvements of cover drainage design as necessary. • Undertake hydrogeological and hydro geochemical modelling of the TSF with emphasis on Cell1 and Surprise Creek. • Installation of seepage mitigation measures developed from 2014 seepage investigation. • Development of cover trials on Cell1.
13 | TSF | Geochemical | Rising acid and/or salts from tailings. | Final cover design or implementation inadequate to control salt migration leading to contamination of final cover growth horizon. | Poor re-­‐vegetation and higher erosion risks leading to potential breach of cover and impacts on terrestrial ecosystems and possibly groundwater. | A conceptual cover design referred to in MRM 2013a. | As above
14 | TSF | Geochemical | Spontaneous combustion of tailings. | Tailings are used in TSF embankment construction and placement in a manner that encourages spontaneous combustion. | Operational heath and safety issues. Localised generation of ARD | The TSF operating guidelines recommend minimising the use of tailings in TSF embankment construction, but the possible use of tailings was mentioned by MRM during site visit. | Review the need for tailings in TSF embankment construction or develop methods of placement that controls spontaneous combustion. | Spontaneous combustion is highly unlikely
15 | TSF | Geotechnical | Storage of tailings and process water | Embankment failure due to instability | Release of tailings and process water into the environment causing impacts to terrestrial and aquatic flora and fauna, sedimentation of Surprise Creek requiring major repair works | Construction QA/QC, visual inspections, monitoring of embankment levels, monthly reports, annual reports | Remove surface water, install embankment piezometers, improve settlement monitoring and monthly reporting to safe operating limits, reanalyse stability based on actual water levels | Daily inspection, Monthly reporting, Annual Dam Safety inspections are in place. Crew numbers increased to ensure adequate staffing. Continuous flow and density monitoring in place and recorded.
16 | TSF | Geotechnical | Storage of tailings and process water | Excessive settlement of the embankment or excessive flooding leading to overtopping | Release of tailings and process water into the environment causing impacts to terrestrial and aquatic flora and fauna, sedimentation of Surprise Creek damage to embankment requiring minor to major repair works | Construction QA/QC, visual inspections, monitoring of embankment levels, monthly reports, annual reports | Remove surface water, improved settlement monitoring and monthly reporting including safe operating limits | Daily inspection, Monthly reporting, Annual Dam Safety inspections are all established. Continuous flow and density monitoring in place and recorded. Water levels monitored daily. Return water system installed on TSF Cell 2 in August to recover water to processing facility.
17 | TSF | Geotechnical | Storage of tailings and process water | Piping through the embankment | Release of tailings and process water into the environment causing impacts to terrestrial and aquatic flora and fauna, sedimentation of Surprise Creek requiring major repair works | Construction QA/QC, visual inspections, monitoring of embankment levels, monthly reports, annual reports | Remove surface water, assess piping potential, install embankment piezometers, improved monitoring and monthly reporting including safe operating limits | Piezometers are to be installed in October 2014. Drilling tenders have been undertaken and the work will be completed as per attachments 18a and 18b. ATC Williams visited site on the 11th to identify proposed locations in the perimeter of cell one and two. This information will be written within the 2014 annual Dam Safety Report
18 | TSF | Geotechnical | Storage of tailings and process water | Piping through the foundation | Release of tailings and process water into the environment causing impacts to terrestrial and aquatic flora and fauna, sedimentation of Surprise Creek requiring major repair works | Construction QA/QC, visual inspections, monitoring of embankment levels, monthly reports, annual reports | Remove surface water, assess piping potential, install embankment piezometers, improved monitoring and monthly reporting including safe operating limits | Daily inspection, Monthly reporting, Annual Dam Safety inspections are in place. Seepage is captured and returned to TSF Cell 2. Continuous flow and density monitoring in place and recorded. Operating according to design specifications.
19 | TSF | Geotechnical | Tailings pipeline | Burst tailings pipeline | Release of tailings and process water into the environment causing impacts to terrestrial and aquatic flora and fauna, sedimentation of Surprise Creek damage to embankment requiring minor repair works | Visual inspections of the pipeline, monitoring of wear and reporting | Remove surface water, assess piping potential, install embankment piezometers, improved monitoring and monthly reporting including safe operating limits | Daily inspection and Monthly reporting in place. Pipeline wall thickness inspections completed annually. Bolts all checked and retorqued, expansion joints all checked and set to specification in August 2014. Rubber lined steel has pipe rating significantly higher than maximum pump pressure achievable. Burst disc installed at transition from steel to poly section at dam wall, directing flow into TSF.
20 | TSF | Geotechnical | Storage of tailings and process water | Seepage through embankment or the foundation | Release of process water into the environment causing impacts to terrestrial and aquatic flora and fauna | Construction QA/QC, visual inspections, monitoring of embankment levels, monthly reports, annual reports | Remove surface water, assess piping potential, install embankment piezometers, improve settlement monitoring and monthly reporting | Daily inspection, Monthly reports, Annual Dam Safety inspections and flow monitoring are in place. Water returned to processing plant when possible via newly installed return line. New valve system being arranged on off-takes around perimeter wall to replace use of spades and promote ease of changing pour point.
21 | TSF | Geotechnical | Storage of tailings and process water | Poor operation, monitoring or management leading to overtopping | Release of tailings and process water into the environment causing impacts to terrestrial and aquatic flora and fauna, sedimentation of Surprise Creek damage to embankment requiring minor to major repair works | Construction QA/QC, visual inspections, monitoring of embankment levels, monthly reports, annual reports | Remove surface water, install embankment piezometers, improved reporting, safe operating limits, monitoring checklists including trigger values for pore pressures, freeboard, seepage and erosion, remedial action plans, documentation of remedial actions | Daily inspection, Monthly reporting, Annual Dam Safety inspections are in place. Dam Safety inspection completed by certified Engineer in September 2014 to check conditions in preparation for the coming wet season. Continuous flow and density monitoring in place and recorded. Water levels monitored daily. Return water system installed on TSF Cell 2 in August to recover water to processing facility. New valve system being arranged on off-takes around perimeter wall to replace use of spades and promote ease of changing pour point.
22 | TSF | Geotechnical | Storage of tailings and process water | Embankment failure due to excessive erosion due to wave action | Release of tailings and process water into the environment causing impacts to terrestrial and aquatic flora and fauna, sedimentation of Surprise Creek requiring major repair works | Construction QA/QC, visual inspections, monitoring of embankment erosion, monthly reports, annual reports | Remove surface water, improved monitoring checklists including trigger values for pore pressures, freeboard, seepage and erosion, remedial action plans, documentation of remedial actions | Daily inspection, Monthly reporting, Annual Dam Safety inspections are in place. Dam Safety inspection completed by certified Engineer in September 2014 to check conditions and list remedial actions as required. Solids beaching against internal perimeter walls or levels extremely shallow thereby limiting wave action.
23 | TSF | Fauna | Clearing of vegetation for construction of TSF cell 4 | Removal of feeding habitat for Gouldian finches | reduced habitat for Gouldian Finches, possible disturbance of Gouldian finches if nesting in surrounding hills | Preliminary Gouldian finch survey conducted in 2013 | Conduct Gouldian finch surveys as part of annual mine site bird surveys, Survey surrounding hill sides for potential breeding habitat, conduct surveys according to guidelines outlined in the EPBC Survey Guidelines for Australia's threatened birds. | Cell 4 project on hold - not planned for 2015,2016
24 | McArthur River | Water Balance Modelling | Deterioration in mine site seepage and/or runoff water quality beyond current estimates Cause is changes in the AMD from the NOEF. This may be due to 1) changes in the PAF/NAF ratio and/or 2) changes in the chemical reactions occurring. | Uncontrolled releases of contaminated water from mine site to McArthur River and/or controlled releases that do not comply with the water quality criteria of the discharge license | Acute and/or chronic adverse impact on riverine and/or marine flora and/or fauna | none | Scenarios need to be included in the water balance modelling to assess the impact and develop a management plan to mitigate this impact. | a) The EIS has a specific team working on developing comprehensive site-wide groundwater and surface water models that can predict the quantity and quality of mine affected waters. Various scenarios with sensitivity runs for key parameters are planned as part of this work. Remediation plans for the existing NOEF are being formulated, with preliminary options already passed onto the DME. MRM are reviewing the KCB report to identify the preferred solutions from the options such as levees, capping of faces, and cut-off trenches.
25 | McArthur River | Water Balance Modelling | The climate in the vicinity of the mine is wetter than that experienced historically. Water balance modelling has assumed the climate from 1889 to the present is representative of the future climate over the life of the mine. The impact of a wetter climate has not been assessed. Further, the impact of one or more years of extreme rainfall has not been assessed. These would be considered rare events with or without climate change. | Uncontrolled releases of contaminated water from mine site to McArthur River and/or controlled releases that do not comply with the water quality criteria of the discharge license | Acute and/or chronic adverse impact on riverine and/or marine flora and/or fauna | none | Scenarios need to be included in the water balance modelling to assess the impact and develop a management plan to mitigate this impact. | MRM have commissioned consultants WRM Water and Environmental to prepare the 2014/2015 annual water balance report for the McArthur River Mine and Bing Bong Loading Facility . The proposed scope of work is: • Undertake a site visit to MRM (17-18/9/14) to inspect and understand the current water management systems and discuss with site personal any changes proposed during the reporting period. • Collect, collate and review available surface water quantity and quality data for the MRM and BBPF sites, especially the data collected since July 2013. • Review the current and proposed MRM and BBPF water demands and supply sources and prepare conceptual flow charts for confirmation by site personnel. • Develop detailed GOLDSIM models for the current and proposed 2014/2015 site conditions at MRM and BBPF, including the latest WDL conditions. • Calibrate the GOLDSIM model against the latest available data, for the previous 12 month reporting period. • Run the GOLDSIM models and collate results for MRM and BBPF for the 12 month reporting period ending June 2014. • Develop site annual water balances for 2014/2015 site conditions at MRM and BBPF. • Review and respond to issues raised by the Independent Monitor. • Prepare a report describing the methodology and results of the water balance modelling suitable for submission to the regulator. Remediation plans for the existing NOEF are being formulated, with preliminary options already passed onto the DME. MRM are reviewing the KCB report to find suitable solutions, including options such as levees, capping of faces, and cut-off trenches. KCB and WRM are constructing a comprehensive site-wide water model as part of the EIS covering both ground and surface water to predict what quantities and qualities of waters may be generated from the operating areas for a range of scenarios. This data will inform the EIS plans.
26 | McArthur River | Water Balance Modelling | The water balance model fails to accurately predict site water balance under changed site conditions. | Uncontrolled releases of contaminated water from mine site to McArthur River and/or controlled releases that do not comply with the water quality criteria of the discharge license | Acute and/or chronic adverse impact on riverine and/or marine flora and/or fauna | Annual revision of the water balance model. Continual improvement in the monitoring of water balance components. | Substantial additional effort in model calibration, reporting and monitoring to identify the most sensitive parameters. Steps taken to reduce the parameter uncertainty based upon the prioritisation of their sensitivity.
27 | River diversions | River diversion design performance | Mine levee wall | A greater than >500 ARI flood event leading to erosion of mine levy wall. | Flooding of the pit from McArthur River resulting in reduced volume of water downstream in McArthur River impacting downstream ecosystems. | Implementation of the revised Early Flood Warning System Procedure. The revised early flood warning system establishes relationships between flood levels at gauges and flood hazard benchmarks (spill way and mine levee) (Document Reference Number: ADM-­‐ENV-­‐PRO-­‐6040-­‐0011). The Site Emergency Response Plan has been updated to include procedure for flooding in the Mine Pit (Document Reference Number: GEN-­‐GEN-­‐PLN-­‐6040-­‐0001). | All proposed actions have been implemented.
28 | River diversions | River diversion design performance | Erosion at toe of mine levee wall and along unplanned overland flow path from the old McArthur River Channel into diversion channel. | Flood flows returning to river from the direction of the remnant river channel. |  | Flow path conditions are examined after each wet season. After erosion experienced in 2009-­‐2010 wet season, rock armouring works were considered to be necessary to address that scour and they were subsequently undertaken in 2010. | Following completion of the 2010 rock armouring works it was found that both the 2010/2011 and 2011/2012 wet season flows caused only minor erosion. It is recommended that this are be re-­‐assessed for erosion potential and reported on. | Undocumented inspections of mine levee wall suggest minimal erosion has occurred due to flooding since 2011/12. Minimal erosion observed in unplanned flow path from old McArthur channel due to rock armouring works undertaken in 2010. Reporting of this issue in annual Environmental Mining Reports are proposed.
29 | River diversions | River diversion design performance | Poor drainage design and bunds formed by mine access roads | Ponding of water between channel and mine bund. | Increased seepage through shallow soil zone and mobilisation of salts impacting terrestrial and aquatic ecosystems. | Small diameter pipes (<100mm) pipes to allow drainage | Previous recommendation -­‐ Reshape area to ensure no ponding of water occurs. It is recommended that this are be re-­‐assessed for erosion potential and reported on. | Possibilities to minimise ponding in severe cases to be assess in 2015. Minor drainage works may be undertaken to alleviate sever ponding areas. Small diameter pipe would likely not be installed owing to possible sedimentation.
30 | River diversions | River diversion design performance | Major erosion/failure of river diversions channel during flood. | Flood event. | Altered flood behaviour. Increased sediment load downstream in the McArthur River. Impact on aquatic and terrestrial ecosystems. | Taking of photographs -­‐ post wet season -­‐ along both banks at 250 metre spacing. Informal assessment of ALS topography and aerial photographs. | Formal assessment of the erosion photographs is not evident. Whereas the ALS topography appears to have been assessed the findings of this assessment are not evident. It is recommended that a formal, documented assessment of the ALS, aerial photographs and site photographs, combined with a visual inspection of key risk areas is conducted annually. | It is proposed to undertake a more comprehensive erosion and geomorphological assessment in yearly in 2014 which will incorporate review of annual ALS data.
31 | River Diversions | River diversion revegetation | Slow revegetation of McArthur River diversion | Flooding in wet season causes erosion and soil redistribution on unvegetated areas. Removal of planted vegetation by flooding and trampling/grazing by feral herbivores | Channel banks are unstable with erosion occurring, reduced riparian habitat, lack of shade for aquatic species, facilitating the spread of weeds | Annual revegetation monitoring, Fences surrounding diversions to exclude feral herbivores, use of coir logs to create soil pockets and tubestock planting. | Target planting efforts at soil pockets resulting from flood water redistribution of soils and soil captured by coir logs. Reassess fencing design to include flood proofing. Ensure annual maintenance is conducted on fencing after the wet season and conduct mustering of cattle within mine area. Ensure fencing encapsulates all of diversion banks. Undertake erosion assessment reports, as committed in PER. | The MRM Rechannel Vegetation Monitoring programme is conducted on an annual basis. The 2014 monitoring was carried out by vegetation specialists between 1-10 9/14 at selected sites located upstream, downstream and within the diversion channels of the McArthur River and Barney Creek. Components of the monitoring programme include but are not limited to: • Development of a completion criteria as an agreed standard or level of performance, which demonstrates successful closure of a site; • Collection of qualitative and quantitative data using conventional survey techniques • Statistical analysis and interpretation of data collected over time • Comparison between analogue and revegetated sites to evaluate establishment and function is on the right trajectory towards the desired end point for relinquishment and closure. • Provide information and mitigation for ongoing rehabilitation including target location, plant species e.g.. floods and assessing disturbance by cattle. The perimeter fence has been redesigned in consultation with DPIF and fencing contractors are scheduled to commence works on 22/9/14
32 | River Diversions | Terrestrial fauna and flora | Creation of unsuitable habitat along Barney Creek and McArthur River diversion channels | Planting of plant species along Barney Creek and McArthur River diversion channels not found at control sites, failure of growth of tubestock and seeds, infestation of weeds. | Different vegetation community than that found up and downstream of channels, unsuitable habitat for fauna. | Key and Primary species for riparian habitats identified. Table provided in Riparian Bird monitoring report detailing suitable riparian plant species. Propagation of riparian flora in MRM nursery | Reassess Key and Primary species list using current analogue sites as a reference or investigate use of different control sites. Include flora species highlighted as important for riparian bird species in the Riparian bird monitoring reports in Key and Primary species. Increase survey sites on the Barney diversion and McArthur River diversion on the downstream halves of the diversions | MRM does not agree to reassess the Key and Primary Species list. The current species list was developed using information collected from surveys conducted along the McArthur River and Barney Creek since 2005 and represent local native species. MRM actively propagate and relocate grass species that have been indentified as key habitat for the riparian bird indicator species. Additional monitoring sites were established included in the 2014 vegetation monitoring program
33 | River Diversions | Aquatic flora and fauna | Inadequate, slow or incorrect rehabilitation of the McArthur River and Barney Creek and Little Barney Creek diversions | River diversion rehabilitation creates poor quality aquatic habitat and a physical /biological barrier to fish migration. | Loss of in stream habitat, changed flow regimes and reduced water quality leads to lower diversity and abundance of aquatic fauna in the diversions. Lack of shelter means predation rates are high. No "edge" macro invertebrate community. Fish, especially marine migrants including freshwater sawfish, are unable to migrate through the diversion to breed or disperse, impacting upstream fish communities. | Freshwater Sawfish Monitoring and Management Programme in place. Aquatic fauna monitoring takes places twice annually. Revegetation of diversions to increase shade and habitat in the future. Addition of large woody debris to improve fish habitat and provide resting areas for fish migrating through the diversion. | Continue to add and monitor large woody debris. Continue to add coir logs to provide additional habitat for fish and capture sediment. Consider additional habitat creation options, such as adding smaller woody debris, boulders and other devices such as hessian barriers. Increase the number of fish monitoring sites on Barney and Little Barney creeks to assess the impacts of these diversions on fish fauna. | Large woody debris is ongoing and recognised as a successful strategy and following the recommendations made in the MRM Aquatic fauna monitoring program. Logs, root buttresses and other woody debris continue to be stockpiled (i.e. they are no longer burnt) by MRM for use in the diversion. In consultation with the aquatic fauna specialist. Additional sites were surveyed for aquatic fauna along Barney and Surprise Creek in the late dry season of 2013 MRM. It should also be noted that a number of the sites listed by the IM are highly seasonal and only contain water during the wet season. Several of these listed sites are dry by the early dry season when sampling of aquatic fauna occurs. Water in the Little Barney Creek Diversion (and the remnant of the original Little Barney Creek) is highly seasonal and dries soon after cessation of the rainfall. In terms of fish, sampling can be incorporated into the early dry season survey of the aquatic monitoring program; however, it is likely that few sites will be available for sampling as the Little Barney Creek Diversion essentially only contains water when it rains and few (if any) remnant pools will exist. Furthermore, the Barney Creek and Little Barney Creek diversions are not considered comparable to the McArthur River diversion in terms of size, hydrology and the fauna present. It is subsequently felt that data collected from naturally vegetated sections of the McArthur River remain the best comparison in terms of measuring recovery in the McArthur River diversion. MRM does do not commit to adding Little Barney Creek to the current monitoring program
34 | PACRIM, ROM and TSF | Terrestrial flora | Fugitive dust emissions from Pacrim Yard and ROM Pad. Dust migration from unvegetated TSF. Dust transported to vegetation by air or as run-­‐off | Heavy metal loads in vegetation, soils and sediments causing vegetation die-­‐back | loss of plants, reduction of habitat for flora and fauna, compromised success of rehabilitation areas, compromised stability of diversion banks, contamination of waterways, mortality of aquatic fauna. | Dust monitoring program, sediment monitoring, vegetation monitoring, dust mitigation measures at mine site including water spray trucks, Introduction of double-­‐lipped rubber lining to sides of PACRIM conveyors. Roller doors installed on concentrate storage shed, sediment traps at Barney Creek diversion bridge. Cell 1 of TSF capped and seeded with shrubs and grass. | testing of heavy metals in vegetation in addition to current aquatic fauna heavy metal monitoring program. | The current vegetation monitoring program includes quantitative assessment of canopy cover which is an early indicator of environmental stress.
35 | Groundwater Resource | Groundwater supply | Poor operation of bore fields and dewatering systems | Over abstraction of groundwater | Over pumping, resulting in depletion of the groundwater resource, aquifer depressurisation, subsidence, reduced groundwater quality | Groundwater monitoring, groundwater modelling | All proposed actions have been implemented | Implement improved monitoring of the MIMEX bore field. Investigating options to increase dewatering from inside the mine levee wall to reduce inflow of groundwater into the pit and also supply raw water meaning a minimisation of groundwater resource use outside the mine levee wall. It is proposed to undertake hydrogeological assessments annually in the Environmental Mining Report for groundwater abstraction and depressurisation by the mine hydro geologist. Revising site wide groundwater modelling during EIS works
36 | McArthur River | Water management | Poor management of excess dirty/contaminated water | Release of dirty/contaminated water | Discharge of excess dirty/contaminated water to the McArthur river, impacting aquatic ecosystems | Groundwater monitoring, surface water monitoring, MRM discharge calculation tool | All proposed actions have been implemented
37 | Water storages | Water storage design | Poor water storage design/construction | Release of dirty/contaminated water | Seepage of dirty/contaminated water, impacting groundwater quality and aquatic and terrestrial ecosystems where groundwater is discharged to creeks/rivers or to the surface | Storage design, seepage monitoring, surface water monitoring and groundwater monitoring | Lining of all storages | MRM constructed the SEPROD PAF dam during 2013. The construction method used a rock shell with a compacted clay liner. The design effort, specifications and level of QA/QC far exceed any dam built by the mine to date. An as-built report was completed to certify the construction. The future planned EPROD and WPROD dams are following this same process to ensure their liners function as planned. A report into the lining of the original NOEF PAF dam (called SPROD) to reduce seepage has been produced, with the activities budgeted for 2015.
38 | Open Pit | Geochemical | Pit water quality after closure. | Oxidation of exposed pyritic PAF and NAF materials in pit walls leading to development of poor pit water quality. | Seepage of contaminated water, impacting groundwater quality and aquatic and terrestrial ecosystems where groundwater is discharged to creeks/rivers or to the surface | Preliminary water balance modelling | Carry out dynamic water and solute balance modelling and assess the potential impacts on groundwater, surface water and directly to flora and fauna. Develop options for post closure pit lake management. | Work commenced on this during 2013 however several uncertainties existed with groundwater models. This work will commence again during the EIS process using a more robust groundwater model
39 | Bing Bong Port | Concentrate Storage | Management of stored concentrate | Discharge of metalliferous/low pH water | Seepage of contaminated water, impacting groundwater quality and aquatic and terrestrial ecosystems where groundwater is discharged to creeks/rivers/sea or to the surface | Operation of containment system (lined drains, paved catchments, lined containment ponds), groundwater monitoring, surface water monitoring | All proposed actions have been implemented
40 | Bing Bong Port | Heavy metals | Storage of concentrate and transfer of concentrate to MV Aburri barge at Bing Bong Port | Spillage and dust emissions of concentrate from on sites storage and during barge load out causes contamination of marine and terrestrial environment with metals | Contamination of seawater and sediments with metals in the swing basin, shipping channel and surrounding area. Biota in the area bioaccumulate metals with unknown lethal and/or sub-­‐lethal/ chronic effects | Dust monitoring programme and dust mitigation measures. Annual marine monitoring of heavy metals in seawater, sediments and biota. Fully contained conveyor system at the loading facility. Dust extractor and positive pressure differential in concentrate shed to minimise dust emissions. Watering roads to minimise dust kicked up by vehicles | Include additional monitoring sites in the annual marine monitoring program immediately west of Bing Bong Port to determine how far contaminants are travelling in the prevailing westerly currents. Include adult fish in the annual marine monitoring program to better understand how fish are being impacted by operations. Investigate dust and spillage minimisation measures being utilised at best practice facilities to minimise dust and spillage, and implement them at Bing Bong Port | A Tapered Element Oscillating Micro Balance (TEOM) has been purchased to provide continuous data logging of dust at Bing Bong. The TEOM is planned to be commissioned in 2014 and this unit will provide compliment the portable monitoring units currently in use. The TEOM and portable units meet Australian standards for measuring ambient air quality. The annual marine program was reviewed in 2012 to include additional sampling sites in the McArthur River mouth (Carrington Channel) and Mule Creek, and two additional sites to the west of Bing Bong (i.e. Bing Bong Creek and Pine Creek) due a net westerly movement of water currents being present in the area.
41 | Bing Bong Port | Flora | Dredging operations and regular passage of the MV Aburri barge. | Dredging and regular passage of the MV Aburri increases sedimentation and turbidity in the waters around Bing Bong Port. | Increased sedimentation smothers seagrass and/or increased turbidity reduces photosynthesis of seagrass, leading to a loss of seagrass coverage, density and/or diversity. This then impacts seagrass dependent communities, such a dugong. | Annual seagrass monitoring program with control sites to determine the relative importance of impacts from MRM's operations and natural phenomena (e.g. cyclones). Seawater quality monitoring. Dredge spoil settled in ponds on land to minimise impacts of dredging on turbidity. | Continue with current monitoring, but establish more suitable control sites, so better baseline data can be collected. Investigate the possibility of incorporating data from long establish national park on sir Edward Pellew Islands, Barranyi National Park, and newly declared Yanyuwa Indigenous Protected Area. | Coastal modelling was carried out in 2013 so the potential migration of sediment transported from the Bing Bong facility could be identified. This modelling informed the location for review of the sample site selection. The li-Anthawirrayarra sea rangers have assisted in both seagrass and annual marine monitoring program. MRM wish to continue collaboration with the sea rangers.
42 | Bing Bong Port | Hydrocarbon storage | Management of stored hydrocarbons | Release of contaminated water | Seepage of NAPL and aqueous phase hydrocarbons, impacting on groundwater quality and aquatic and terrestrial ecosystems where groundwater is discharged to creeks/rivers/sea or to the surface | Containment system design, hydrocarbon audits, inspection procedures, monitoring of storages | Installation of high level alarm on storages | Day tank at Bing Bong now has an overflow return line running back into the main diesel tank. Main diesel tank is fully bunded with any runoff reporting to the wheel wash sump which in turn reports to the Site runnoff pond
43 | Bing Bong Port | Surface water | Overflow of Bing Bong surface runoff pond (BBSRP) | High rainfall/storm event, or failure to clean out sediment from pond. Mismanagement of water volumes | Poor quality water (metals, acid) affect terrestrial and aquatic ecosystems | 3 adjacent surface runoff containment ponds. Annual water balance modelling undertaken. Evaporation of pond water through use of pond water as dust suppression across site. Annual marine heavy metal monitoring. Trucks transporting water to TSF (as previously required) | All three runoff ponds should be cleaned out and emptied as far as practicable prior to the wet season. Design report for the runoff ponds to be reviewed by the Independent Monitor. Confirmation that water balance modelling will be undertaken annually. | Pond 1 contains water year round and cannot be 'cleaned out'. Ponds 2 and 3 are cleaned as seasonal conditions allow. Ponds 2 and 3 are fully lined with HDPE and have interconnected surface pumping infrastructure that allows for water to be moved between ponds 2 & 3. Ponds 2 & 3 are cleaned out prior to wet season and collected rainfall is pumped out of these ponds before ant water is transferred from Pond 1 The Bing Bong Loading Facility is included in annual water balance reports.
44 | Bing Bong Port | Dust migration | Concentrate storage at Bing Bong Port | Emissions of dust from the Bing Bong Port concentrate storage shed and road vehicles to the marine environment | Heavy metal contamination of seawater, marine sediments and potentially marine biota | Dust monitoring program and dust mitigation measures including maintenance of a positive pressure differential and dust extractor system in the concentrate shed to reduce dust fugitive emissions, dust-­‐suppressing sprinkler systems on roads and vehicle wash down facilities |  | A Tapered Element Oscillating Micro Balance (TEOM) has been purchased to provide continuous data logging of dust at Bing Bong. The TEOM is planned to be commissioned in 2014 and this unit will provide compliment the portable monitoring units currently in use. The TEOM and portable units meet Australian standards for measuring ambient air quality
45 | Mine Site and Bing Bong Load-­‐ out Facility | Weed management | Infestation of weeds | Weeds present on mine leases from historical mining and pastoral activities are colonising cleared areas uncolonised by native vegetation. | Weed infestations exclude native vegetation and reduces habitat for fauna. | Weed Management Plan in place with targeted weed control carried out with liaison from Weeds District Officer. Parkinsonia biological control trials at Bing Bong dredge spoils. | Follow Weed Management Plan. Investigate employment and training of local residents from Borroloola in weed management. Include control of Passiflora foetida in future Weed management plans, continue to investigate possibility of cooperative weed control with pastoral properties upstream on McArthur River. | MRM Indigenous Employment Program currently offers employment for rehabilitation activities that include some weed management. Passiflora foetida is not declared under the NT Noxious Weeds Act 2003 and therefore is not a priority for weed control . MRM conducts aerial spray programs that cover upstream of the mine lease area and within the McArthur River Pastoral Station
46 | Bing Bong load-­‐ out facility | Fauna | Dust migration or concentrate spillage from Bing Bong Port | Bioaccumulation of metals in small marine crustaceans and fish | Heavy metal bioaccumulation in food sources of migratory birds causing poisoning affecting important migratory bird and wader populations. | Monitoring of heavy metals in sediments and biota. Bi-­‐ annual Migratory Bird surveys. Dust monitoring and control measures implemented including sprinkler system at port | Further reduce dust emissions from Bing Bong Port e.g. by enclosing concentrate shed. Continue monitoring migratory bird populations. | As per the MRM Open Cut Mining Project approvals (EPBC 2003/954 Condition 3), a Migratory Wader and other Bird Monitoring Plan was required for a minimum of 5 years. McArthur River Mine has completed a substantial amount of surveys since 2007 and to date there have been no reports or significant changes attributed to mining activities. Whilst it is still accepted that long term monitoring data on migratory shorebirds and waders are important for assessing the impacts it is proposed to change the current plan to occur every 5 years instead of annually
47 | Bing Bong Dredge Spoil | Drainage | Potential for acid sulphate soils around the outer spoon drain. | Acid sulphate soils exposed by excavation of the outer spoon drain, which causes acid leachate. | Local impacts on re-­‐vegetation, water quality. | None | Carry out acid sulphate soil assessment of spoon drain and other potential sources at Bing Bong | Soil samples collected adjacent to the Bing Bong Dredge Spoil are analysed in the annual Bing Bong Vegetation and soil assessment program. Furthermore beach sediment surveys are conducted annually to identify potential pathways for acid sulphate. There is no reporting of acid sulphates in the receiving environment as a result of the Bing Bong operations from all surveys
48 | Bing Bong Dredge Spoil | Dredge spoil pond management | Management of entrained dredge spoil water | Release of marine water | Seepage of marine water from the dredge spoil ponds, impacting groundwater quality and aquatic and terrestrial ecosystems | Operation of drainage system on and around the ponds, groundwater monitoring, surface water monitoring | All proposed actions have been implemented | A Dam Safety Review is currently underway for this facility. ATC Williams completed the field inspection on the 11 of September 2014. As per below comments
49 | Bing Bong Dredge Spoil | Geotechnical | Storage of dredge spoil and seawater | Embankment failure due to instability | Release of sediment and sea water into the environment causing impacts to terrestrial and aquatic flora and fauna requiring major repair works -­‐ most likely during active discharge | Construction QA/QC, visual inspections, monitoring of embankment levels, monthly reports | Install embankment piezometers, improve pore pressure, settlement, erosion and other monitoring and reporting, set and assess performance against safe operating limits (incl. freeboard), routine maintenance and repairs | MRM commissioned engineering consultants to conduct the 2014 dam safety inspection at Bing Bong . The inspection will be carried out against the ANCOLD guidelines (May 2012), with the purpose of this inspection is to systematically assess the ongoing/future integrity of each of the cells/storages.MRM plan to develop a life of mine dredge spoil dump plan. This will include relevant design, monitoring, QA/QC and safety specifications. These specifications will be adopted in detailed design and operations plan of next stage of dredge spoil dump development. The components of the include but not limited to • a current hazard assessment; • an audit of existing documentation on the dam; • a review of structural, hydraulic, hydrological and geotechnical design aspects; • a review of historical operational records; and • a review of surveillance reports. Based on the above, the scope of the works carried out was as follows: • Identification of any areas of concern/deficiencies; • review of surveillance/monitoring data, as available, against observed conditions to identify the potential onset of any unfavourable or concerning condition; and • Assessment of appropriate actions to address any concerns/deficiencies to ensure the ongoing effective and safe operation of the cells. MRM will consider any recommendations made in the engineering report due for delivery 30th October 2014. MRM plan to develop a life of mine dredge spoil dump plan. This will include relevant design, monitoring, QA/QC and safety specifications. These specifications will be adopted in detailed design and operations plan of next stage of dredge spoil dump development.
50 | Bing Bong Dredge Spoil | Geotechnical | Storage of dredge spoil and seawater | Excessive settlement of the embankment or excessive flooding leading to overtopping | Release of sediment and sea water into the environment causing impacts to terrestrial and aquatic flora and fauna, damage to embankment requiring minor to major repair works -­‐ most likely during active discharge | Construction QA/QC, visual inspections, monitoring of embankment levels, monthly reports | Invoke a high frequency of visual, settlement and freeboard monitoring during active discharge, undertake maintenance and repairs before and after active discharge
51 | Bing Bong Dredge Spoil | Geotechnical | Storage of dredge spoil and seawater | Piping through the embankment | Release of sediment and sea water into the environment causing impacts to terrestrial and aquatic flora and fauna requiring major repair works -­‐ most likely during active discharge | Construction QA/QC, visual inspections, monitoring of embankment seepage monthly reports | Invoke a high frequency of visual, settlement and freeboard monitoring during active discharge, undertake maintenance and repairs before and after active discharge
52 | Bing Bong Dredge Spoil | Flora | Sections of Dredge spoil left unvegetated and use of incorrect seed mix in revegetated areas | Areas of dredge spoil left unvegetated due to use for cells for storage of future dredging spoils. Area of cells revegetated as seeded with incorrect species. Spoil material is difficult for non-­‐salt tolerant species to establish on | Alteration or loss of habitat, creation of dust | Previous monitoring by orthophoto mapping and ground truthing of vegetation. CDU PhD student began revegetation trials on a section of the spoil but was not completed. Vegetation monitoring within cell 1. Area of dredge spoil ponds reseeded with grasses in 2011. | Continue with rehabilitation of dredge spoils -­‐ utilise landscaping of cells to promote veg growth despite future dredge plans. Use seed mixes consisting of salt tolerant species present in the coastal habitat surrounding the spoil. Monitor dust creation from the dredge spoils. | Salt tolerant grass species will be direct seeded subject to future dredging activities.
53 | Bing Bong Dredge Spoil | Flora | Drain surrounding dredge spoil not protecting habitat surrounding dredge spoil from highly saline water | Seepage of highly saline water from dredge spoil into undisturbed habitat surrounding dredge spoil, seawater being retained for extended periods by drain bund wall or previous obstruction of creek line to the east of the spoil | Dieback of vegetation in undisturbed habitat surrounding the dredge spoil and alteration to flora adapted to very saline soils and/or extended periods of inundation by seawater | Annual maintenance of drain which drains saline water out to sea. Annual vegetation monitoring of vegetation surrounding spoil area. South west corner of dredge spoil removed | Continue vegetation monitoring program. Inspect outside wall of drain for pooling of seawater and log in monthly inspections. Conduct remedial works if pooling is identified | The Bing Bong Dredge Spoil vegetation condition and soil monitoring program commenced in 2012 and carried out each year since. Monitoring in 2014 was completed in July . MRM are currently awaiting delivery of the final report.
54 | Bing Bong dredge spoil | Dust migration | Concentrate loading onto MV Aburri and from MV Aburri onto export vessels | Fugitive dust emissions to the marine environment | Heavy metal contamination of seawater, marine sediments and potentially marine biota | Dust monitoring program and dust mitigation measures covered conveyor belts at the loading facility to minimised fugitive dust emissions during loading of concentrate to the MV Aburri |  | MRM have monitored marine sediment, water and selected biota from sites in the vicinity of the Bing Bong Loading Facility has occurred since 1998 with the main aim being to provide ongoing data to identify whether contaminants were being introduced into the marine ecosystem during MRM operations. In 2012 the program was reviewed with the aim to increase the consistency of samples collected between sites and robustness of the data set. This included the addition of sampling sites in the McArthur River mouth (Carrington Channel) and Mule Creek, and two additional sites to the west of Bing Bong (i.e. Bing Bong Creek and Pine Creek) due a net westerly movement of water currents being present in the area. Additional biota was also collected including the Bluetail Mullet (Valamugil buchanani) when present. Furthermore, the Green Mud crab (Scylla cerrata) and the molluscs Terebralia semistriata and Telescopium telescopium were collected from as many sample sites as possible. The Bing Bong marine monitoring program is conducted on an annual basis. The program has included studies in the transhipment are in 1992, 1993,1996, 2003, 2005, 2007, 2010, 2012,& 2013. A wet scrubbing system was installed on MV Aburri during Singapore Dry Docking 2014 which captures all cargo hold fumes. This is in addition to the cargo bay and all conveyors being covered.
55 | Transhipment Area | Heavy metals | Transfer of concentrate from MV Aburri barge to larger vessel in the transhipment area | Load out from the MV Aburri to larger transport causes dust emissions and spillage of concentrate, which contaminate the marine environment with lead and zinc | Contamination of seawater and sediments with metals in the transhipment area and surrounds. Biota in the area bioaccumulate metals with unknown lethal and/or sub-­‐lethal/ chronic effects | Nil | Ensure appropriate control are in place, including covered/closed load out systems, to minimise dust and spillage. Include the transhipment area in the annual marine monitoring program. If seagrass is present in the area, include the transhipment area in the seagrass monitoring program.
56 | Sir Edward Pellew Islands and McArthur River Estuary | Heavy metals | Mining operations adjacent to McArthur River and its tributaries. Operations at Bing Bong Port. | Contaminants entering McArthur River travel downstream and settle in sediments around the McArthur River estuary and Sir Edward Pellew Islands. Dust travels across from Bing Bong Port | Bioaccumulation of metals in sediments and biota in vicinity of McArthur River estuary and Sir Edward Pellew Islands. Unknown sub-­‐lethal/ chronic effects, effects on higher trophic species (including humans that eat fish caught from the area) | Numerous controls at Bing Bong Port and MRM to minimise dust emissions, seepage and spills, including fully contained loading systems, watering of roads and seepage capture drains. Monitoring of contamination of soils, dust, fluvial sediments, surface water and groundwater around McArthur River mine and Bing Bong Port. Monitoring of contaminants in seawater, marine sediments and biota at Bing Bong Port and surrounds, McArthur River estuary and Sir Edward Pellew Islands. | Continue current monitoring and controls
57 | Sir Edward Pellew Islands, McArthur River and Bing Bong Port | Vibrios bacteria | Operations at MRM | Mining and associated activities leads to an increase in zinc concentrations in waters and sediments at the McArthur River estuary and Sir Edward Pellew Island. Zinc leads to and increase in Vibrios bacteria. | Vibrios bacteria may infect local population with necrotising fasciitis (flesh eating bacteria syndrome), leading to severe illness and, in some cases, death. | Vibrios monitoring. Monitoring water and sediments for zinc contamination. | Final monitoring Vibrios program should be conducted in 2015. If there is no change in results from the previous three surveys, then there is likely no relationship between MRM and Vibrios bacteria | Vibrios studies have been conducted for four consecutive years and concluded that Vibrios represented a very small percentage of the total microbial diversity at the study sites and while more than one species was detected, there was no evidence for an association with metals or of mine influence
58 | Vehicular transport fleet | Dust emissions | Loading of concentrate onto transport vehicles at the mine site/transport of concentrate to Bing Bong Port | Fugitive dust emissions during loading and transport | Loss of water and sediment quality and increased dust deposition rates | Extensive dust monitoring program and dust mitigation measures including covered dust generation points, Water addition point to the head drum of the stockpile feed conveyor, booster pump and spray bar for the head drum, watering around the general area by water trucks, use of water sprays in the primary crushing plant and conveyors, double layered skirting on horizontal rubber guarding, dust extraction system fitted to the secondary tertiary crusher building, wash down of all vehicles prior to leaving the mine site for Bing Bong Port and other destinations, maintenance of a positive pressure differential and dust extractor system in the concentrate shed, a street sweeper which is planned to be used around the site and in particular the concentrator to remove any fugitive emissions which have settled to the ground |  | Existing controls are all functional. MRM have purchased a TEOM to be installed in 2014 which will provide continues monitoring of fugitive dust and supplement the data collected by existing portable dust monitors.
59 | PACRIM and ROM | Dust emissions | Dust blown from ROM Pad and Pacrim yard causes loss of water and sediment quality and loss of flora/ fauna in Barney creek flood plain | Fugitive dust emissions from Pacrim Yard and ROM Pad. | Mobilisation of salts and metals impacting terrestrial and aquatic ecosystems. | Dust mitigation measures at mine site including Water spray trucks. Introduction of double-­‐lipped rubber lining to sides of PACRIM conveyors. | Crushing facility is to be relocated and will be further away from Barney Creek. Risk remains until the crushing plant is removed. | The crushing facility has been relocated. A TEOM has been purchased for installation between the new crushing facility and Barney Creek.
60 | Mine Site | Geochemical | Indications of acid, saline and metal leaching issues not identified. | Indicators of mine affected drainage not identified due to inadequate assessment of results and interpretation of trends and/or Insufficient monitoring points and/or frequency. | Issues associated with management of acid/saline/metal leaching materials not identified early enough to modify management and prevent impacts on groundwater, terrestrial and aquatic ecosystems. | KCB reviewed surface water and groundwater quality in 2014 integrated with geochemical assessment. | Build on KCB 2014 work with a specific monitoring review to feed back into acid/saline/metal leaching materials management. Surface water monitoring, groundwater monitoring, and field checks of dump materials should be included in the review, and assessed for any indications of geochemical impacts. The need to modify monitoring locations and frequency should also be assessed. Carry out additional surface water and ground water monitoring along the northern and eastern edge of the NOEF as recommended by KCB (2014b). | An extensive monitoring bore installation campaign is programmed for October 2014 in conjunction with KCB. This will include in the order of 50 new monitoring locations, many of them being paired wells to investigate different depths in the profile. This will include: • Numerous bores adjacent to the NOEF perimeter where seepage has been ponding and beside the proposed Central West expansion to monitor any impacts. • Away from the NOEF to gather baseline data, assist with future designs and improve groundwater contouring. • Within the NOEF to assess seepage mounding within the dump and water quality underneath the dump. • Around the proposed WPROD to gather baseline data. • Adjacent to the TSF embankments to identify seepage preferential pathways and assist modelling of hydrogeological processes. • Away from the TSF to delineate the contaminant plume, gather baseline data and improve groundwater contouring. • Between the mine levee wall and the diversion to improve understanding in this area and identify any impacts. Analyses of soils cores are proposed for several locations adjacent to the TSF and NOEF to determine contamination and parameters associated with contaminant transport and retention. It is expected that a through review of the monitoring program and development of future monitoring strategies will be undertaken in conjunction with EIS works..
61 | Mine Site | Geochemical | Potentially acid, saline and metal leaching materials are used for construction purposes across site. | Materials used in construction previously classified NAF may now be a geochemical hazard under the new criteria. Material types used in construction not adequately tracked. | Local impacts on re-­‐vegetation, water quality. | None known. | Prepare an inventory of waste rock placement areas across site outside of the NOEF and review material classification. Carry out further geochemical testing as requited to assess the acid, saline and metal leaching potential of each area. | Geology resources have been identified to complete this in 2014.
62 | Mine site | Fauna | Fugitive dust emissions and seepage as a result of operations. | Dust emissions from the TSF, haul roads and other aspects of operations and seepage from the TSF and NOEF affects water and fluvial sediment quality in McArthur River and Barney, Little Barney and Surprise Creeks. | Reduction in water quality reduces diversity and abundance of aquatic fauna. Metals bioaccumulate in aquatic fauna causing unknown lethal and/or sub-­‐lethal/ chronic effects. Contaminants then migrate downstream from MRM. | Dust emission controls, such as watering roads and a clay cap on TSF cell 1. Drains constructed around TSF and NOEF to capture seepage. Monitoring dust, contaminants in fluvial sediments, water quality, aquatic fauna diversity and abundance and assessing bioaccumulation of metals in fish around MRM. Routine inspections of infrastructure. | Expand dust mitigation measures, such as additional silt traps on the Barney Creek bridge that are regularly emptied and increased spraying of roads. Expand the metal monitoring in freshwater fauna along Barney Creek to identify exactly where contaminants are entering waterways so sources of contamination can be isolated and identified. | A TEOM is installed adjacent to the Barney Creek bridge which provides continues data on dust levels generated by heavy vehicle movement. The unit has an alert system which is relayed when dust levels are elevated. In August 2014 the Birney Creek Sediment complex was engineered design and constructed with the aim to collect surface runoff water reporting to the Barney Creek haul road bridge are, settle out solids and discharge the clean water to the Barney Creek. The system includes the SE sump which follows on from work done on the NW corner of this complex in Q1 2014.
63 | Mine site | Fauna | Infrastructure, pipelines etc, on site. | Infrastructure fails on site, leading to contamination of waterways with metals and salts. | Reduction in water quality reduces diversity and abundance of aquatic faun. Metals bioaccumulate in aquatic fauna causing unknown lethal and/or sub-­‐lethal/ chronic effects. This then migrates downstream from MRM. | Regular inspections and maintenance of infrastructure. Regular water and sediment monitoring, annual monitoring of metals and other contaminants in aquatic fauna. | NIL
64 | Mine Site | Fauna and flora | Fragmentation of habitat | Cleared or areas slow to revegetate leave patches of open land between vegetated areas. | The lack of vegetation cover prevents the movement of small fauna including small mammals, reptiles and grass birds. | Planting of tubestock, bi-­‐annual riparian bird surveys, annual vegetation surveys along diversions | Leave vegetation corridors where possible. | Environmental survey is conducted on all clearing permits.
65 | Mine site | Soil monitoring | Lack of appropriate soil monitoring | Insufficient spatial density and poor optimisation of analytes. | Contamination of particular areas is not noticed | Limited soil sampling program. | Upgrade soil monitoring program to include areas of sampling not currently covered by the current monitoring program and reflect the requirements of the revised NEPM (1999). | MRM will review the annual soil monitoring program in 2015 to include areas that may influenced by an expansion of the mine footprint e.g. NOE,F and interpret results against the revised NEPM Guidelines (2003)
66 | Mine site | Hydrocarbon storage | Management of stored hydrocarbons | Release of contaminated water | Seepage of NAPL and aqueous phase hydrocarbons, impacting on groundwater quality and aquatic and terrestrial ecosystems where groundwater is discharged to creeks/rivers or to the surface | Containment system design, hydrocarbon audits, inspection procedures, monitoring of storages, groundwater monitoring | Installation of high level alarm on storages | New fuel farm design includes real time monitoring of fuel filling and includes high and low level alarms. The new fuel farm is to be installed in Q4 2014
67 | Mine site | Security bonds | Mine closure liability | MRM Closes unexpectedly, leaving NOEF, TSF, river diversions, and mine site rehabilitation unfinished. | Sudden closure results in shortfall in materials to complete rehabilitation resulting in increased costs and bond unable to cover cost. | Revegetation has started on river diversions, monetary bond in place. | OEF should be progressively rehabilitated to confirm that cover design is appropriate and will work. Improve closure model calibration (i.e., costs, materials balance etc.) to confirm assumptions in the model. Implement TSF Cell 1 interim cover design and/or final cover design. Closure plan should include contingencies for sudden closure. | a) The commencement of progressive rehabilitation of the dump that was planned for 2014 has been delayed by the MMP process. Progressive rehabilitation activities will now be postponed until the EIS refines the options for the halo and cover portions of the dump. Trials are likely to be conducted first to test alternatives, with more extensive rehabilitation left until MRM establishes an approved closure plan for the dump. b) The EIS will specify a new closure plan for the mine site that reflects the latest waste rock and tailings geochemistry knowledge. Estimates of the rehabilitation cost to achieve the approved plan will then be provided using specialist knowledge where required to ensure the costs are robust. c) The options for remediating TSF Cell 1, which include covers and reprocessing, are being evaluated. Confirming existing and finding additional materials for constructing the TSF covers is included in the scopes for the EIS team. d) The closure plan will be updated as part of the EIS, with this item to be included.
68 | Mine site | Security bonds | NOEF | Reclassification of waste rock results in insufficient material being available to construct a cover over the NOEF that can be demonstrated to be stable in the long term (period to be agreed between MRM and DME) and consequently all waste rock is required to be returned to the open pit. | Significant financial impact. Unknown what if any impacts may occur by backfilling open pit. | No controls currently in place as backfilling of pit with waste rock not currently being considered. | Additional investigations into material balance and cover design options to determine if a cover can be constructed which will provide long term stability which is acceptable to all stakeholders. If backfill (or partial backfill) the only option additional groundwater investigations to determine likelihood of contaminated water seeping from open pit back into McArthur River. | a) Investigations into the design and specifications of covers, and material balances to enable them to be constructed, are key outcomes required from the EIS. The fieldworks that are commencing in October are set to improve the confidence in the resources of various materials. Comprehensive water management investigations and modelling will be required for every option put forward for closing the site, including options that may backfill the pit.